## D202 Project Plan
D202 - Hidden Treasure Plan
Start Date: 03/09/10, Deadline: 05/11/10 |  | Estimated Timings |  |  | Actual Timings |  |  | Class/ Home | Comments on progress
Lessons per week: 5.5, Lesson length: 60 minutes
Main Task | Sub Tasks | Start Date | Finish Date | Lessons Allowed | Start Date | Finish Date | Lessons Taken
Introduction
| Read the project brief carefully | 2010-09-03 | 2010-09-03 | 1 | 2010-09-03 | 2010-09-03 | 1 | Class
Create project folders
Planning/ keeping track
| Create initial plan | 2010-09-03 | 2010-09-06 | 2 | 2010-09-03
Create assets table
Proposal
| Create proposal document with my ideas for my treasure hunt | 2010-09-07 | 2010-09-07 | 1
Map
| Design the map | 2010-09-08 | 2010-09-08 | 1
Create the map
Update assets table
Game Instructions
| Create instructions | 2010-09-09 | 2010-09-09 | 1
Teacher Checkpoint
Task 1 - The Puzzles
| Produce a storyboard for the puzzles | 2010-09-10 | 2010-09-10 | 1
Create primary assets
Create the puzzles
Update assets table
Task 2 - The Animation
| Create a timeline storyboard for the animation | 2010-09-13 | 2010-09-13 | 1
Produce the animation
Get feedback from test users
Update assets table
Task 3 - The Movie
| Create a timeline storyboard for the movie | 2010-09-14 | 2010-09-14 | 1
Produce and edit the movie
Get feedback from test users
Update assets table
Coding Sheet
| Create the coding sheet | 2010-09-15 | 2010-09-15 | 1
Teacher Checkpoint
Eportfolio
| Create new Dreamweaver site | 2010-09-16 | 2010-09-16 | 1
Create and link Eportfolio pages
Check all links work
Ask test buddy for feedback
Teacher Checkpoint
Contingency
| Extra time to make sure everything is complete | 2010-09-17 | 2010-09-17 | 1
Project Review
| Get feedback from teacher on treasure hunt and overall progress | 2010-09-17 | 2010-09-17 | 1
Complete project review
Add review to Eportfolio
Teacher Checkpoint
|  |  |  | 13 | lessons planned |  | 1 | lessons taken
Formulas:
Finish Date = VLOOKUP([Lessons Allowed],' '!A1:B62,2)
Finish Date = VLOOKUP(E6+[Lessons Allowed],' '!A1:B62,2)

## 
1 | 2010-09-03
2 | 2010-09-03
3 | 2010-09-06
4 | 2010-09-07
5 | 2010-09-08
6 | 2010-09-09
7 | 2010-09-10
8 | 2010-09-13
9 | 2010-09-14
10 | 2010-09-15
11 | 2010-09-16
12 | 2010-09-17
13 | 2010-09-17
14 | 2010-09-20
15 | 2010-09-21
16 | 2010-09-22
17 | 2010-09-23
18 | 2010-09-24
19 | 2010-09-27
20 | 2010-09-28
21 | 2010-09-29
22 | 2010-09-30
23 | 2010-10-01
24 | 2010-10-01
25 | 2010-10-04
26 | 2010-10-05
27 | 2010-10-06
28 | 2010-10-07
29 | 2010-10-08
30 | 2010-10-11
31 | 2010-10-12
32 | 2010-10-13
33 | 2010-10-14
34 | 2010-10-15
35 | 2010-10-15
36 | 2010-10-18
37 | 2010-10-19
38 | 2010-10-20
39 | 2010-10-21
40 | 2010-11-01
41 | 2010-11-02
42 | 2010-11-03
43 | 2010-11-04
44 | 2010-11-05
45 | 2010-11-05
46 | 2010-11-08
47 | 2010-11-09
48 | 2010-11-10
49 | 2010-11-11
50 | 2010-11-12
51 | 2010-11-15
52 | 2010-11-16
53 | 2010-11-17
54 | 2010-11-18
55 | 2010-11-19
56 | 2010-11-19
57 | 2010-11-22
58 | 2010-11-23
59 | 2010-11-24
60 | 2010-11-25
61 | 2010-11-29
62 | 2010-11-30